## Changes
Sarbon - Company tariffs / registration / overview / chat / invitations / web-calls - 18.07.2026
Admin company tariffs+limits. Full-profile company registration. Company overview (all ~30 fields + requisites + deletion banner). Company team chat reused over real /chat + calls. Identity-based employee invitations + in-app offers card + driver-invite mode + role dropdown fixes. Dispatcher invitation bell. Company offers polling. Chat call duration humanized. WebRTC answer-path SDP + camera/mic release. 90+ files / 3 commits + working-tree.
# | Type | Area | Change | Endpoint / detail | Screenshot
1 | FEATURE | Admin / Tariffs | Creator-only Tariffs tab (catalog list/create/edit/default) + per-company Assign-tariff modal: assigning copies the tariff limits into the company (existing companies unaffected by later edits); over-quota is a warning. Company limits change ONLY via tariff, not direct max_* PATCH. Pure tariffs.ts + tests | POST /v1/admin/companies/:id/tariff {tariff_id} | 01-admin-tariff-create, 02-admin-assign-tariff
2 | FEATURE | Company / Registration | Company create form expanded from 3 fields to a full profile (contacts, legal/director, bank details) - all optional; only name, type and INN (9-digit STIR / 14-digit PINFL) required. Create already returns a company-scoped token pair; optionals sent via a follow-up PATCH | POST /v1/companies + PATCH | 03-company-create-profile
3 | FIX | Company / Overview | Overview showed only ~8 of ~30 GET /v1/companies/:id fields. Added requisites card, owner (with "you" badge), tariff, updated_at; merged fleet+limits into one quota card (usage + limit, over-quota mark); all dates -> Tashkent; single empty placeholder. Redesigned deletion-request banner (amber Trash2 chip + withdraw). Pure companyOverview.ts + tests | GET /v1/companies/:id, DELETE deletion-request | 04-company-overview, 05-company-overview-dark
4 | FEATURE | Company / Chat | Company team chat = the real dispatcher ChatPage reused at /company/chat/:companyId (sidebar, media, voice/video notes, CALLS), made surface-aware via useChatIdentity + chatSurface.ts (company token under /company/*; /chat byte-identical). Cards switch-on-click via useCompanyOpen | /company/chat/:companyId, /v1/chat/* | 06-company-chat
5 | FEATURE | Company / Invitations | Moved employee invites from deprecated link/token to identity-based model: invite by phone -> 201 {id, status:pending} + in-app invitation_offer; invitee reads GET /company-users/offers, accepts by id. New "Invitations for you" card (Accept/Decline) on company home. must_register_first (404) / already_member (409) handled | POST /v1/invitations/:id/accept¦decline, GET /company-users/offers | 07-invitation-offers-card
6 | FIX | Company / Role dropdown | companyRoleI18nKey normalizes casing (ALL-CAPS / PascalCase / SNAKE_CASE all resolve) so labels no longer render "Cargomanager"; parseInvitableCompanyRoleOptions keeps only company_user_roles employee roles and always drops Owner/Carrier/Driver; SHIPPER type-gate hides driver/fleet roles | GET /v1/reference/company | 08-invite-role-dropdown, 09-invite-role-gating-shipper
7 | FEATURE | Company / Driver invite | Employee¦Driver toggle in the invite modal: Driver mode hides the role dropdown and submits phone-only to the separate driver endpoint (permission fleet.driver.manage, all 3 company types). Driver accepts in the driver app. buildCreateDriverInvitationPayload + driverInvitationErrorCode (+7 tests) | POST /v1/companies/:id/driver-invitations {phone} | 10-driver-invite
8 | FEATURE | Dispatcher / Notifications | Dispatcher notification bell now renders the invitation_offer type (was invisible to invited CM/DM): "Company invitation" tag, Building2 icon, localized "{inviter} invited you to join {company} as {role}", "Open invitation" CTA -> /:lang/company, explicit SSE handler + OS notification | invitation_offer (SSE + trip-notifications) | 11-dispatcher-invitation-bell
9 | FIX | Company / Offers | Company Offers (pending-approval) and per-cargo offers only revalidated on the 60s staleTime; company surface has no realtime bridge. Added polling + refetch-on-focus (staleTime 15s, refetchInterval 20s, refetchOnWindowFocus true) so a bid landing while a manager sits on the page appears | GET /v1/companies/:id/offers/pending-approval | 12-offers-polling
10 | FIX | Chat / Call duration | Conversation-list preview showed a call duration as raw seconds "(73s)" instead of "1 min 13 sec"; preview now rebuilt client-side (formatChatCallEventPreview) to match the thread bubble and follow current language. Sub-minute calls drop the "0 min" prefix -> "22 sec" (new durationSecondsLabel in all 15 locales) | ConversationItem, chatCallEvents.ts | 13-chat-call-duration-sidebar, 14-chat-call-duration-thread
11 | FIX | Web calls / WebRTC | Answer (callee) path mobile->web: web ANSWER was a=recvonly audio + a=msid:- video (freeze/silence); forceVideoSendrecv now setStreams (real msid) + new forceAudioSendrecv/findAudioTransceiver re-assert both m-lines before createAnswer, so the 300kbps/20fps cap takes effect. Also: camera/mic now released unconditionally on endCall (was skipped on 409/error) + reconcile guard covers ended | webrtcTuning.ts, GlobalAudioCallModal.tsx | (protocol/media - no UI; verify-webrtc-answer-sdp.mjs)

## Verification
Verification gates
Gate | Result
tsc -b (full project type-check) | exit 0
vitest run | 1950 / 1950
eslint --max-warnings 0 + prettier (changed files) | clean
Locale parity | 15/15 (company.* / admin.* / tripNotifications.* en/uz/ru + placeholders)
Runtime verification (per fix) | 14 new qa/verify-*.mjs, 0 console errors
WebRTC answer-path SDP (verify-webrtc-answer-sdp.mjs) | both m-lines sendrecv + real msid
Adversarial / code-review follow-ups | findings addressed
Files touched | 90+ (3 commits + working-tree)